## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
1 | User Authentication (Login & Registration) | As a user, I want to register and log in to the system with my username and password,so that I can securely access my financial data. | Must have | 1 | 1. Users can enter their usernames and passwords. 2. Passwords are encrypted for security. 3. Users are redirected to their dashboard after successful login. | 5 | User login is a critical feature for ensuring secure access to the system. It should have proper validation, encryption, and robust error handling. Focus on making the login process simple and secure, with clear error messages for failed login attempts. | 2025.3.28 | 2025.4.2
2 | CSV File Data Import | As a user, I want to upload transaction record files in CSV format, so that the system can automatically read and categorize my financial data. | Must have | 1 | 1. Users can choose to upload CSV files for import. 2. Users can select a file to upload, and the data is automatically parsed into the system. 3. If the file is in an incorrect format, the system displays an error message. | 4 | The CSV import feature should ensure data consistency and ease of use. Validate the file format before importing, and provide clear instructions for users on how to format their CSV files. This feature is essential for users who want to bulk-upload transactions. | 2025.3.28 | 2025.4.2
3 | AI-Based Transaction Categorization | As a user, I want the system to automatically categorize my transactions using AI, so that I can save time on manual categorization. | Must have | 2 | 1. The AI correctly categorizes 80% of transactions. 2. Users can override the AI’s categorization. 3. AI classification accuracy is tracked and continuously improved. | 8 | AI-based transaction classification needs to be highly accurate. Implement continuous improvement based on user feedback. The system should allow users to manually adjust classifications and log these changes to improve future predictions. | 2025.4.2 | 2025.4.6
4 | Expenditure Category Customization | As a user, I want to customize the expenditure categories according to my personal needs, so that I can track my spending more effectively. | Must have | 2 | 1. Users are enabled to add new expenditure categories. 2. Users are permitted to delete unnecessary expenditure categories. 3. The system allows for modification of existing categories. | 3 | Category customization enhances the user experience by allowing personalized financial tracking. Ensure the customization options are intuitive, and users should easily manage, add, and remove categories. Reflect the changes immediately in the system for real-time updates. | 2025.4.2 | 2025.4.6
5 | Budget Suggestions | As a user, I want the system to provide saving suggestions based on my spending habits and allow me to set monthly budgets, so that I can improve my financial health. | Must have | 3 | 1. The system generates savings suggestions based on past spending habits. 2. Users can set and manage monthly budgets. 3. Users receive notifications when exceeding the budget. | 6 | Important for user engagement, as suggestions need to be specific and actionable. | 2025.4.7 | 2025.4.11
6 | Monthly Expense Report Generation | As a user, I want the system to generate a monthly expense summary, so that I can track my spending and make informed financial decisions. | Must have | 3 | 1. The system generates monthly expense summary reports. 2. Users can view detailed spending categories (e.g., groceries, entertainment, utilities). 3. Users can export reports in formats like CSV or PDF. | 7 | The monthly expense summary provides a snapshot of the user's financial health. Ensure the summary is clear, concise, and accessible. Users should be able to quickly identify trends in their spending and adjust their behavior accordingly. The option to export data ensures that users can store and analyze reports outside the system. | 2025.4.7 | 2025.4.11
7 | Notification for Budget Alerts | As a user, I want to receive notifications when my spending exceeds my budget, so that I can take immediate action to stay on track. | Should have | 4 | 1. The system detects high spending beyond budget. 2. Users receive notifications (in-app or via email) when the threshold is breached. 3. The system offers suggestions on how to reduce overspending and stay within the budget. | 4 | Budget alerts serve as a safety net to ensure users don't overspend. Timely notifications help users stay aware of their financial limits, and suggestions for cost-cutting provide actionable steps for saving. Alerts should be customizable to meet users' preferences for frequency and urgency, making the system flexible. | 2025.4.11 | 2025.4.16
8 | Recurring Bill Management | As a user, I want the system to automatically identify my recurring bills (e.g., monthly utilities, rent, etc.) and notify me, so that I can better plan my budget. | Should have | 4 | 1.The system automatically identifies recurring bills through transaction pattern analysis. 2.Users can manually add, edit, or delete recurring bills. 3.The system sends a reminder 3 days before the bill is due. 4.Budget suggestions explicitly account for recurring bills to help users allocate their budget effectively. | 4 | Recurring bills are a core part of users' fixed expenses and directly impact budget planning and savings goals.Common recurring expenses for Chinese users (e.g., utilities, rent, credit card payments) require tailored management. | 2025.4.11 | 2025.4.16
9 | AI-based Transaction Classification Optimization | As a user, I want the system to continuously improve its AI-based transaction classification, so that I experience fewer misclassified transactions and save time correcting them. | Should have | 5 | 1. The classification accuracy improves to over 95%. 2. The need for manual corrections by users is reduced. 3. User feedback is used to continuously improve the classification algorithm. | 4 | Continuous improvement is key for AI-based features. By optimizing the classification system, we ensure that users spend less time correcting AI mistakes. Learning from user corrections will refine the AI model and improve the overall user experience, making the system more intuitive and efficient over time. | 2025.4.16 | 2025.4.21
10 | Localized Financial Context (China-specific) | As a user in China, I want the system to provide localized budgeting recommendations and adjust for seasonal spending habits, so that I can better manage my finances according to local trends. | Should have | 5 | 1. The system provides budgeting recommendations tailored for the Chinese market. 2. It adjusts for seasonal spending patterns like those during Chinese New Year. 3. Users receive recommendations based on local economic conditions and trends. | 5 | China-specific financial recommendations are essential to address the unique spending habits influenced by regional events and holidays. By accounting for Chinese New Year and other cultural factors, users will receive relevant, localized financial advice for better budgeting and spending. | 2025.4.21 | 2025.4.26
11 | Automated Data Cleaning | As a user, I want the system to periodically clean outdated or invalid transaction data, so that my financial records stay accurate and the system remains efficient. | Should have | 6 | 1. The system automatically identifies and removes outdated or invalid transaction data. 2. Users are notified whenever data is cleaned or removed. 3. Data cleaning occurs at scheduled intervals to keep the system running smoothly. | 3 | Data cleaning ensures the accuracy and efficiency of the system. By automatically removing invalid or outdated data, the system prevents data bloat and ensures that the user’s records remain accurate. Notifying users ensures transparency and keeps them informed of any data changes. | 2025.4.26 | 2025.4.30
12 | Daily Budget Reminders | As a user, I want to set daily reminders for my budget, so that I can stay on track with my daily spending limits. | Should have | 6 | 1. Users can set daily reminders for their spending limits. 2. Alerts are triggered when users exceed the daily limit. 3. The system allows users to customize the frequency of reminders (e.g., daily, weekly). | 2 | Daily reminders will keep users engaged and help them manage daily spending. Customizable reminder frequency allows users to set reminders based on their preferences, making it easier to stay within budget limits. | 2025.4.26 | 2025.4.30
13 | Export Financial Data | As a user, I want to export my financial data into CSV or PDF format, so that I can keep personal records and share my finances with others. | Should have | 7 | 1. Users can select CSV or PDF format for exporting their financial data. 2. Users can specify a date range for the data export (e.g., last month, last year). 3. The system generates a clean and well-formatted report in the selected format. | 4 | Export features are essential for personal record keeping, sharing data with others, or generating reports for financial reviews. Ensure that exports are clearly formatted and include necessary details, such as spending categories and total amounts. | 2025.5.1 | 2025.5.6
14 | Spending Analytics and Reports | As a user, I want the system to generate visual spending charts and financial reports for different time ranges, so that I can easily analyze my spending and savings over time. | Should have | 7 | 1. The system generates annual, monthly, or custom time-range spending charts based on user data. 2. The charts are visually clear, easy to interpret, and customizable to meet user preferences. 3. The system generates comprehensive financial reports that include insights into spending and savings, providing detailed analysis over different time periods. | 6 | Graphs and reports are designed to be visually clear and meaningful to users, helping them make informed financial decisions. A well-organized summary with easy-to-read charts will empower users to understand where their money is going and make adjustments as needed. | 2025.5.1 | 2025.5.6
15 | Yearly Financial Summary | As a user, I want the system to generate an annual financial summary report, so that I can review my yearly spending, income, and savings at a glance. | Could have | 8 | 1. The system generates an annual financial summary. 2. The summary includes detailed analysis of spending, income, and savings over the year. 3. The report is downloadable in PDF format for easy access and sharing. | 5 | This feature provides users with a yearly overview of their finances, highlighting trends and helping with long-term financial planning. The PDF export ensures that users can easily share or store their annual summary for record-keeping. | 2025.5.7 | 2025.5.13
16 | Multi-Account Management | As a user, I want to manage transaction records from multiple accounts (e.g., bank accounts, Alipay, WeChat Pay), so that I can keep track of all my financial activities in one place. | Could have | 8 | 1. Users can add and manage multiple accounts (bank, Alipay, WeChat Pay, etc.). 2. Each account is managed separately, with its transactions tracked independently. 3. The system allows users to easily switch between accounts to view records. | 7 | Multiple account management is necessary for users who use various payment systems, ensuring they can consolidate their financial data in one place. The ability to switch between accounts effortlessly helps users manage their finances more efficiently. | 2025.5.7 | 2025.5.14
17 | User Feedback Submission | As a user, I want to submit feedback within the application, so that I can report errors or provide suggestions for improving the system. | Could have | 8 | 1. Users can submit feedback through an easy-to-fill form. 2. Users can attach screenshots or other files to better explain their issues or suggestions. 3. The feedback is stored securely for review and analysis by the development team. | 3 | Feedback should be easy for users to provide, with clear instructions for submitting suggestions or reporting problems. This mechanism is essential for continuous system improvement, as it helps developers understand user concerns and needs. | 2025.5.7 | 2025.5.15
18 | Language Switching Support | As a user, I want to be able to switch between different languages (e.g., Chinese, English), so that I can use the application in my preferred language. | Could have | 9 | 1. Users can select a language preference from the available options (e.g., Chinese, English). 2. The system automatically switches to the selected language. 3. All user interface elements (text, buttons, menus) are correctly localized and translated. | 6 | Multi-language support ensures the application is adaptable to international users. This feature enhances accessibility and usability for a global audience, making the app more inclusive and scalable in future releases. | 2025.5.13 | 2025.5.18
19 | Two-Factor Authentication for Login | As a user, I want to secure my account with two-factor authentication (2FA), so that I can ensure my login is protected from unauthorized access. | Want to have | 10 | 1. The system prompts users to enter a verification code as part of the login process. 2. Users input the code sent via their preferred method (SMS, email, or authentication app). 3. Login proceeds only after successful 2FA verification. | 8 | Protecting user accounts is vital to ensure data security. Implementing a reliable 2FA solution will add an extra layer of security to user accounts, reducing the risk of unauthorized access. Consider offering multiple 2FA methods for user convenience. | 2025.5.20 | 2025.5.25
20 | Future Spending Forecast | As a user, I want the system to provide budget analysis and forecast future spending, so that I can better plan my finances based on historical spending trends. | Want to have | 10 | 1. The system uses historical spending data to predict future spending trends. 2. The system provides detailed analysis of spending patterns to help users identify potential cost-saving areas. 3. The analysis is easy to understand and helps users adjust their future budgets accordingly. | 5 | Predicting future spending based on historical data adds significant value to the application. It helps users plan ahead, set more accurate financial goals, and make informed decisions to stay within their budget. The feature can enhance user engagement by providing actionable insights. | 2025.5.20 | 2025.5.25